## Project Template
Project | Pick-Up Sportz |  |  |  |  | Project Manager |  | Chaz Del Prato
Project Start Date |  | Start of Fall Semester 2019 |  |  |  | Project End Date |  | End of Spring Semester 2020
Task |  | Task Type | Task Status | Est SLOC | Actual SLOC | Priority | Assigned To | Assigned Date | Deadline | Estimated Hrs | Start Date | End Date | % Done | Actual Hr.
Populate Sprint Board |  | Sprint #0 | Completed |  |  | High | Chaz Del Prato, Benjamin Seo, Brandon Le, John Him, Jamil Khan, Christine Duong | 2019-08-28 | 2019-09-18 | 2 | 2019-08-26 | 2019-09-18 | 100% | 3
Product Details |  | BRD | Completed |  |  | Medum | Chaz Del Prato | 2019-08-28 | 2019-09-18 | 1 | 2019-08-26 | 2019-09-18 | 100% | 1
Preface |  | BRD | Completed |  |  | Low | Benjamin Seo | 2019-08-28 | 2019-09-18 | 1 | 2019-09-16 | 2019-09-18 | 100% | 1
Appendix |  | BRD | Completed |  |  | Low | Benjamin Seo | 2019-08-28 | 2019-09-18 | 1 | 2019-09-16 | 2019-09-18 | 100% | 1
Mini Business Plan - Strategy |  | BRD | Completed |  |  | Medum | Brandon Le | 2019-08-28 | 2019-09-18 | 2 | 2019-08-26 | 2019-09-18 | 100% | 1
Mini Business Plan - SWOT Analysis |  | BRD | Completed |  |  | Medum | John Him | 2019-08-28 | 2019-09-18 | 1 | 2019-08-26 | 2019-09-18 | 100% | 1
Mini Business Plan - Market Segment |  | BRD | Completed |  |  | Medum | Brandon Le | 2019-08-28 | 2019-09-18 | 2 | 2019-08-26 | 2019-09-18 | 100% | 2
Mini Business Plan - Primary Market Research |  | BRD | Completed |  |  | High | Benjamin Seo | 2019-08-28 | 2019-09-18 | 5 | 2019-08-26 | 2019-09-18 | 100% | 4
Mini Business Plan - Secondary Market Research |  | BRD | Completed |  |  | High | Chaz Del Prato, Benjamin Seo, Christine Duong, Jamil Khan | 2019-08-28 | 2019-09-18 | 8 | 2019-08-26 | 2019-09-18 | 100% | 6
Mini Business Plan - Comercialization Strategy |  | BRD | Completed |  |  | Medum | John Him | 2019-08-28 | 2019-09-18 | 2 | 2019-08-26 | 2019-09-18 | 100% | 2
Mini Business Plan - Monetization Strategy |  | BRD | Completed |  |  | Medum | John Him | 2019-08-28 | 2019-09-18 | 2 | 2019-08-26 | 2019-09-18 | 100% | 2
Total Solution |  | BRD | Completed |  |  | Medum | Benjamin Seo | 2019-08-28 | 2019-09-18 | 2 | 2019-09-17 | 2019-09-18 | 100% | 1
Gantt Chart |  | MP | Completed |  |  | High | Brandon Le, Christine Duong | 2019-09-11 | 2019-09-23 | 4 | 2019-09-18 | 2019-09-23 | 100% | 1
Project Tracking Matrix |  | MP | Completed |  |  | High | Benjamin Seo | 2019-09-11 | 2019-09-23 | 2 | 2019-09-21 | 2019-09-23 | 100% | 2
Code Development Velocity Calculation |  | MP | Completed |  |  | High | Chaz Del Prato | 2019-09-11 | 2019-09-23 | 0.5 | 2019-09-18 | 2019-09-23 | 100% | 0.5
Sprint Board |  | MP | Completed |  |  | High | Jamil Khan | 2019-09-11 | 2019-09-23 | 2 | 2019-09-18 | 2019-09-23 | 100% | 2
Burndown Chart |  | MP | Completed |  |  | High | Jamil Khan | 2019-09-11 | 2019-09-23 | 3 | 2019-09-18 | 2019-09-23 | 100% | 2
Sprint Retrospective |  | MP | Completed |  |  | High | Benjamin Seo | 2019-09-11 | 2019-09-23 | 1 | 2019-09-21 | 2019-09-23 | 100% | 1
Sprint Review Records in an Appendix |  | MP | Completed |  |  | High | John Him | 2019-09-11 | 2019-09-23 | 3 | 2019-09-21 | 2019-09-23 | 100% | 3
Lessons Learned From Agile Devlopment |  | MP | Completed |  |  | High | John Him | 2019-09-11 | 2019-09-23 | 1 | 2019-09-21 | 2019-09-23 | 100% | 1
Fix Preface - Technology Innovation or Depth |  | BRD | Completed |  |  | Medum | Benjamin Seo | 2019-09-22 | 2019-09-29 | 0.5 | 2019-09-22 | 2019-09-29 | 100% | 0.5
Fix Strategy - Unfair Advantage, Customer Segment, Channels |  | BRD | Completed |  |  | Medum | Brandon Le | 2019-09-22 | 2019-09-29 | 1 | 2019-09-22 | 2019-09-29 | 100% | 1
Fix Competitors |  | BRD | Completed |  |  | Medum | Benjamin Seo | 2019-09-22 | 2019-09-29 | 0.5 | 2019-09-22 | 2019-09-29 | 100% | 0.5
Fix Personas |  | BRD | Completed |  |  | Medum | Brandon Le | 2019-09-22 | 2019-09-29 | 1 | 2019-09-22 | 2019-09-29 | 100% | 1
Create Database |  | Sprint #0 | Completed |  |  | High | Chaz Del Prato | 2019-09-18 | 2019-09-29 | 8 | 2019-09-18 | 2019-09-29 | 100% | 5
Fix Gant Chart |  | MP | Completed |  |  | Medum | Brendon Le, Christine Duong | 2019-09-22 | 2019-09-29 | 1 | 2019-09-22 | 2019-09-27 | 100% | 1
Goals |  | PRD | Completed |  |  | High | Brandon Le | 2019-09-30 | 2019-10-14 | 0.5 | 2019-09-30 | 2019-10-14 | 100% | 0.5
User Personas |  | PRD | Completed |  |  | High | Jamil Khan | 2019-09-30 | 2019-10-14 | 0.5 | 2019-09-30 | 2019-10-14 | 100% | 0.5
User Stories |  | PRD | Completed |  |  | High | Chaz Del Prato | 2019-09-30 | 2019-10-14 | 0.5 | 2019-09-30 | 2019-10-14 | 100% | 0.5
Server Sitemap |  | PRD | Completed |  |  | High | Benjamin Seo | 2019-09-30 | 2019-10-14 | 1.5 | 2019-09-30 | 2019-10-14 | 100% | 1.5
Page Description |  | PRD | Completed |  |  | High | Benjamin Seo | 2019-09-30 | 2019-10-14 | 1 | 2019-09-30 | 2019-10-14 | 100% | 1
Wireframe |  | PRD | Completed |  |  | High | Benjamin Seo | 2019-09-30 | 2019-10-14 | 2 | 2019-09-30 | 2019-10-14 | 100% | 3
Interfaces |  | PRD | Completed |  |  | High | Benjamin Seo | 2019-09-30 | 2019-10-14 | 1 | 2019-09-30 | 2019-10-14 | 100% | 1
Additional Functional Requirements |  | PRD | Completed |  |  | High | Benjamin Seo | 2019-09-30 | 2019-10-14 | 1 | 2019-09-30 | 2019-10-14 | 100% | 1
Non-Functional Requirements |  | PRD | Completed |  |  | High | Benjamin Seo | 2019-09-30 | 2019-10-14 | 2 | 2019-09-30 | 2019-10-14 | 100% | 2
Performance Requirements |  | PRD | Completed |  |  | High | Benjamin Seo | 2019-09-30 | 2019-10-14 | 1 | 2019-09-30 | 2019-10-14 | 100% | 1
Future Iterations |  | PRD | Completed |  |  | Low | Benjamin Seo | 2019-09-30 | 2019-10-14 | 0.5 | 2019-09-30 | 2019-10-14 | 100% | 0.5
Diagrams Section |  | ADD | Completed |  |  | High | Chaz Del Prato, Benjamin Seo | 2019-10-07 | 2019-10-14 | 7 | 2019-10-07 | 2019-10-14 | 100% | 7
Analysis Section |  | ADD | Completed |  |  | High | Benjamin Seo, Brandon Le | 2019-10-07 | 2019-10-14 | 6 | 2019-10-07 | 2019-10-14 | 100% | 6
Create a User Manual |  | Sprint #2 | Completed |  |  | Low | Everyone | 2019-10-21 | 2019-10-30 | 5 | 2019-10-21 | 2019-10-30 | 100% | 5
UI for player Profile |  | Sprint #2 | In-Progress |  |  | High | Everyone | 2019-10-21 | 2019-11-06 | 8 | 2019-10-21 |  | 30%
Back-End Profile Editing |  | Sprint #2 | In-Progress |  |  | High | Everyone | 2019-10-21 | 2019-11-06 | 8 | 2019-10-21 |  | 0%
Test Profile Editing |  | Sprint #2 | In-Progress |  |  | High | Everyone | 2019-10-21 | 2019-11-06 | 2 | 2019-10-21 |  | 0%
Create Functional Website |  | Sprint #2 | Completed |  |  | High | Everyone | 2019-10-21 | 2019-11-06 | 10 | 2019-10-21 | 2019-11-06 | 100% | 10
Search Events on Website |  | Sprint #2 | In-Progress |  |  | High | Everyone | 2019-10-21 | 2019-11-06 | 2 | 2019-10-21 |  | 0%
Test Website Functionality |  | Sprint #2 | Completed |  |  | High | Everyone | 2019-10-21 | 2019-11-06 | 3 | 2019-10-21 | 2019-11-06 | 100% | 3
UI for Login to Website using Pick Up Sportz Account |  | Sprint #2 | Completed |  |  | High | Everyone | 2019-10-21 | 2019-11-06 | 3 | 2019-10-21 | 2019-11-06 | 100% | 3
UI for Login to Website using Google Account |  | Sprint #2 | In-Progress |  |  | High | Everyone | 2019-10-21 | 2019-11-06 | 3 | 2019-10-21 |  | 10%
Back-End Login |  | Sprint #2 | In-Progress |  |  | High | Everyone | 2019-10-21 | 2019-11-06 | 7 | 2019-10-21 |  | 60%
UI for Create Account Features |  | Sprint #2 | Completed |  |  | High | Everyone | 2019-10-21 | 2019-11-06 | 3 | 2019-10-21 | 2019-11-06 | 100% | 3
Back-End Account Creation |  | Sprint #2 | In-Progress |  |  | High | Everyone | 2019-10-21 | 2019-11-06 | 7 | 2019-10-21 |  | 10%
Test Account Creation and Login |  | Sprint #2 | In-Progress |  |  | High | Everyone | 2019-10-21 | 2019-11-06 | 2 | 2019-10-21 |  | 0%
UI for Logout Feature |  | Sprint #2 | In-Progress |  |  | High | Everyone | 2019-10-21 | 2019-11-06 | 2 | 2019-10-21 |  | 0%
Backend-End Logout |  | Sprint #2 | In-Progress |  |  | High | Everyone | 2019-10-21 | 2019-11-06 | 7 | 2019-10-21 |  | 0%
Test Logout Feature |  | Sprint #2 | In-Progress |  |  | High | Everyone | 2019-10-21 | 2019-11-06 | 2 | 2019-10-21 |  | 0%
Connect and Communicate to the Database for all current Features |  | Sprint #2 | Completed |  |  | High | Everyone | 2019-10-21 | 2019-11-06 | 12 | 2019-10-21 | 2019-11-06 | 100% | 12
Test Data Transfer to and from Database |  | Sprint #2 | Completed |  |  | High | Everyone | 2019-10-21 | 2019-11-06 | 4 | 2019-10-21 | 2019-11-06 | 100% | 4
Total Hours Spent |  | 112 |  | Project Progress |  | 82.6316 | %

## Default Fields
Select Project | Select Task | Select Status | Select Priority | Select Project Manager | Select Resource | % Done | Task Type | Est. SLOC | Actual SLOC
Pick-Up Sportz | Product Details | Created | Low | Chaz Del Prato | Benjamin Seo | 0% | BRD
| Preface | Assigned | Medum |  | Brandon Le | 10% | MP
| Appendix | In-Progress | High |  | Christine Duong | 20% | Sprint #0
| Mini Business Plan - Strategy | Completed |  |  | Jamil Khan | 30% | Sprint #1
| Mini Business Plan - SWOT Analysis | Resolved |  |  | John Him | 40% | PRD
| Mini Business Plan - Market Segment | Re-Opened |  |  | Chaz Del Prato | 50% | Code
| Mini Business Plan - Primary Market Research |  |  |  |  | 60%
| Mini Business Plan - Secondary Market Research |  |  |  |  | 70%
| Mini Business Plan - Comercialization Strategy |  |  |  |  | 80%
| Mini Business Plan - Monetization Strategy |  |  |  |  | 90%
| Total Solution |  |  |  |  | 100%
Gantt Chart
Project Tracking Matrix
Management Plan
Code Development Velocity Calculation
Sprint Board
Burndown Chart
Sprint Retrospective
Sprint Review Records in an Appendix
User Review Summary
User Review Analysis and Actions
Lessons Learned From Agile Devlopment